## Evidence
Your Name | Dustin Bramos
Project Name | Golf Player Time Management
Sprint# | Efforts (Hrs) | Towards objectives | Brief Description of Acomplishments | Artifact Name | Location | Reference
Sprint # 1 | 16 | 6[IT] | Researched and wrote the server setup requirement. | Requirements | Sprint 1.docx and Sprint 1.pptx | Page 2 on document and slide 8 on powerpoint
Sprint # 2 | 20 | 6[IT], [3,5], [2] | Helped set up the server environment and designed the database ERD with the team. Set up the ERD portion of the powerpoint presentation. | GPTMS_ERD.mwb and Sprint2.pptx | GPTMS_ERD.mwb and Sprint 2.pptx | GPTMS_ERD.mwb and Database ERD slide on powerpoint
Sprint # 3 | 22 | 6[CS, IT], 5 | Wrote some controllers and helped re plan the structure of the project. | profileQueries.php and profileController.php | profileQueries.php and profileController.php | The code inside the api/User folder.
Sprint # 4 | 35 | 1, 2, 3, 5, 6[CS] | Created the History page's query and helped with controllers. Created a MySQL script to completely fill the database with test data. Made a small change to the ERD. Collaborated on the powerpoint presentation. | userQueries.php, userControllers.php, Sprint4.pptx, Test Data Insertion Script.sql and GPTMS_ERD.mwb | userQueries.php, userControllers.php, Sprint4.pptx, Test Data Insertion Script.sql and GPTMS_ERD.mwb | The query inside userQueries.php, the script inside the test insertion script, the Sprint 4 powerpoint, and the database ERD.
Sprint # 5 | 36 | 1, 2, 3, 5, 6[CS] | Made the querey to pull hole data for score cards and to start a game. Created the controller logic for the hole data, and laid down the framework for the game-management controller logic. Also helped with some of the re-working/design of the database to make it more relation oriented. | CourseMngmntQueries.php, GameMngmntQueries.php, CourseMngmntController.php, GameMngmntController.php, GPTMS ERD.mwb | CourseMngmntQueries.php, GameMngmntQueries.php, CourseMngmntController.php, GameMngmntController.php, GPTMS ERD.mwb | holeSelect function in coursemanagement controller and query files. And the queries inside of the game queries file, along with the basic framework of the game controller file.
Sprint # 6
Sprint # 7
Sprint # 8
Sprint # 9
Sprint # 10
Sprint # 11
Sprint # 12

## Count
Your Name |  | Dustin Bramos
Project Name |  | Golf Player Time Management
Objectives
Sprint# | Team Member | 1 | 2 | 3 | 4 | 5 | 6[CS] | 6[IT]
1 | Dustin Bramos | 2 | 3 | 1 | 1 | 5 | 2 | 3
2 | Dustin Bramos | 0 | 8 | 1 | 0 | 1 | 2 | 10
3 | Dustin Bramos | 0 | 0 | 0 | 0 | 10 | 6 | 6
4 | Dustin Bramos | 10 | 1 | 1 | 0 | 3 | 20 | 0
5 | Dustin Bramos | 12 | 1 | 1 | 0 | 4 | 18 | 0
6 | Dustin Bramos | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Dustin Bramos | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Dustin Bramos | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Dustin Bramos | 0 | 0 | 0 | 0 | 0 | 0 | 0