## Evidence
Your Name | Luis Ramirez
Project Name | Golf Player Time Management System
Sprint# | Efforts (Hrs) | Towards objectives | Brief Description of Acomplishments | Artifact Name | Location | Reference
Sprint # 1 | 17 | 6[CS, IT] | Researched/proposed development environments (IDEs) compatible with possible languages and frameworks to be used. | Sprint 1.doc; Sprint 1.pptx | https://github.com/quentinxs/GPTMS/blob/Luis/docs/sprints/Sprint%201.docx https://github.com/quentinxs/GPTMS/blob/Luis/docs/presentations/Sprint%201.pptx | Page 2-3, Slide 9
Sprint # 2 | 18 | 1, 2, 3, 5, 6[CS, IT] | Designed/created sign up form for users, worked on information for Sprint 2 presentation(class diagram and Quality Assurance tests), and provided user stories. | front-end folder Sprint 2.pptx User Stories.docx | https://github.com/quentinxs/GPTMS/tree/Luis/front-end/src/app https://github.com/quentinxs/GPTMS/blob/Luis/docs/presentations/Sprint%202.pptx https://github.com/quentinxs/GPTMS/blob/Luis/.github/ISSUE_TEMPLATE/User%20Stories.docx | signup folder Slides 3, 5-7 Sprint 2 and 3 stories
Sprint # 3 | 20 | 1, 3, 5, 6[CS, IT] | Continued to design/revise front end UI for users once they are logged in (navigation bar, edit profile, user landing page) and signup/login forms. Assisted with user stories and Sprint 3 presentation | front-end folder Sprint 3.pptx | https://github.com/quentinxs/GPTMS/tree/Luis/front-end/src/app https://github.com/quentinxs/GPTMS/blob/Luis/docs/presentations/Sprint%203.pptx | signup folder, navbar folder, profile folder. Slides 2-3
Sprint # 4 | 16 | 1, 3, 5, 6[CS, IT] | Worked on frontend development of user profile forms, scorecard design. Fixed navbar reponsiveness and routing. Helped with presentation powerpoint. | front-end folder Sprint 4.pptx | https://github.com/quentinxs/GPTMS/tree/Luis/front-end/src/app/navbar https://github.com/quentinxs/GPTMS/tree/Luis/front-end/src/app/profile https://github.com/quentinxs/GPTMS/blob/master/front-end/src/app/play/play.component.html https://github.com/quentinxs/GPTMS/tree/Luis/docs/presentations | navbar folder, profile folder, play folder Slides 2 and 4
Sprint # 5 | 18 | 1, 2, 3, 4, 5, 6[CS, IT] | Worked on frontend development of user profile form, scorecard design, and play form. Attempted connection/routing between front and back end for starting a game | front-end folder | https://github.com/quentinxs/GPTMS/tree/Luis/front-end/src/app/profile https://github.com/quentinxs/GPTMS/tree/Luis/front-end/src/app/history https://github.com/quentinxs/GPTMS/tree/Luis/front-end/src/app/play | navbar folder, profile folder, play folder under Luis branch
Sprint # 6 | 17 | 1, 6[CS, IT] | Worked on frontend development of play form. Attempted connection/routing between front and back end for selecting game settings | front-end folder | https://github.com/quentinxs/GPTMS/tree/Luis/front-end/src/app/play https://github.com/quentinxs/GPTMS/blob/Luis/front-end/src/app/course.service.ts https://github.com/quentinxs/GPTMS/blob/Quentin/front-end/src/app/hole.ts | course.service.ts and hole.ts files, play folder under Luis branch
Sprint # 7 | 16 | 4, 6[CS, IT] | Worked on frontend development of party location and game form functionality. Assisted with security and implementing HTTPS for the application. | front-end folder | https://github.com/quentinxs/GPTMS/blob/Luis/front-end/src/app/game.service.ts https://github.com/quentinxs/GPTMS/blob/Luis/front-end/src/app/game/game.component.html https://github.com/quentinxs/GPTMS/blob/Luis/front-end/src/app/game/game.component.ts | game.service.ts and the play folder in front-end under Luis branch
Sprint # 8
Sprint # 9
Sprint # 10
Sprint # 11
Sprint # 12

## Count
Your Name |  | Luis Ramirez
Project Name |  | Golf Player Time Management System
Objectives
Sprint# | Team Member | 1 | 2 | 3 | 4 | 5 | 6[CS] | 6[IT]
0 | Ramirez, Luis | 0 | 0 | 0 | 0 | 0 | 10 | 6
1 | Ramirez, Luis | 0 | 0 | 0 | 0 | 0 | 8 | 9
2 | Ramirez, Luis | 2 | 2 | 3 | 0 | 3 | 4 | 4
3 | Ramirez, Luis | 1 | 0 | 2 | 0 | 3 | 7 | 7
4 | Ramirez, Luis | 1 | 0 | 2 | 0 | 3 | 5 | 5
5 | Ramirez, Luis | 3 | 2 | 1 | 1 | 1 | 3 | 7
6 | Ramirez, Luis | 0 | 0 | 0 | 1 | 0 | 8 | 8
7 | Ramirez, Luis | 0 | 0 | 0 | 2 | 0 | 8 | 6
8