## Evidence
Your Name | Quentin Sheets
Project Name | Golf Player Time Management System (GPTMS)
Sprint# | Efforts (Hrs) | Towards objectives | Brief Description of Acomplishments | Artifact Name | Location | Reference
Sprint # 1 | 16 | 5,6[IT] | Initiated the team’s repository on GitHub, developed a project plan, contributed to and edited presentation | Sprint 1.docx Sprint 1.pptx | https://github.com/quentinxs/GPTMS/blob/master/docs/sprints/Sprint%201.docx; https://github.com/quentinxs/GPTMS/blob/master/docs/presentations/Sprint%201.pptx | Page 1: Project Plan Sprint1.pptx
Sprint # 2 | 16 | 1,2,3,5,6[IT] | Started angular project for front end, created login module, conducted meetings between front and back end development | front-end/ Sprint 2.pptx | https://github.com/quentinxs/GPTMS/tree/master/front-end https://github.com/quentinxs/GPTMS/blob/master/docs/presentations/Sprint%202.pptx | front-end/ Sprint 2.pptx
Sprint # 3 | 20 | 1,3,5,6[IT] | Initiated multiple modules and class models for front end, created first service connection to back end endpoint, conducted meetings between front and back end development to resolve miscommunication | front-end/src/app/ auth.service.ts Sprint 3.pptx | https://github.com/quentinxs/GPTMS/tree/master/front-end/src/app https://github.com/quentinxs/GPTMS/blob/master/front-end/src/app/auth.service.ts https://github.com/quentinxs/GPTMS/blob/master/docs/presentations/Sprint%203.pptx | front-end/src/app/ auth.service.ts Sprint 3.pptx
Sprint # 4 | 18 | 1,4,5,6[IT] | Added two more service connections to back end endpoints, Populated front end pages with data from server, worked with back end to resolve merge conflicts and CORS issue that arose, helped write user stories for next sprint | user.service.ts course.service.ts front-end/src/app/ UserController.php GitHub Issues/Story Board | https://github.com/quentinxs/GPTMS/blob/master/front-end/src/app/user.service.ts https://github.com/quentinxs/GPTMS/blob/master/front-end/src/app/course.service.ts https://github.com/quentinxs/GPTMS/tree/master/front-end/src/app https://github.com/quentinxs/GPTMS/blob/master/api/users/UserController.php https://github.com/quentinxs/GPTMS/projects/1 | user.service.ts course.service.ts front-end/src/app/ Lines 2-17 Story Board / Issues
Sprint # 5 | 18 | 4,5,6[IT] | Fixed error in guard removing ability of non-authenticated users to see certain pages, added map and scorecard to course page, started admin module, | auth.guard.ts app/course-detail app/admin | https://github.com/quentinxs/GPTMS/blob/master/front-end/src/app/auth.guard.ts https://github.com/quentinxs/GPTMS/tree/master/front-end/src/app/course-detail https://github.com/quentinxs/GPTMS/tree/master/front-end/src/app/admin | Lines 10-17 app/course-detail app/admin
Sprint # 6 | 18 | 4,5,6[IT] | Added cards to dashboard page, started on course management page, assisted Jakob on in-game scorekeeping, connected signup component to backend endpoint | app/landing app/manage-course app/game user.service.ts | https://github.com/quentinxs/GPTMS/tree/master/front-end/src/app/landing https://github.com/quentinxs/GPTMS/tree/master/front-end/src/app/manage-course https://github.com/quentinxs/GPTMS/tree/master/front-end/src/app/game https://github.com/quentinxs/GPTMS/blob/master/front-end/src/app/user.service.ts | app/landing app/manage-course app/game user.service.ts
Sprint # 7
Sprint # 8
Sprint # 9
Sprint # 10
Sprint # 11
Sprint # 12

## Count
Your Name |  | Quentin Sheets
Project Name |  | Golf Player Time Management System (GPTMS)
Objectives
Sprint# | Team Member | 1 | 2 | 3 | 4 | 5 | 6[CS] | 6[IT]
1 | Quentin Sheets |  |  |  |  | 2 |  | 1
2 | Quentin Sheets | 1 | 1 | 1 |  | 1 |  | 1
3 | Quentin Sheets | 1 |  | 1 |  | 1 |  | 1
4 | Quentin Sheets | 1 |  |  | 1 | 1 |  | 3
5 | Quentin Sheets |  |  |  | 2 |  |  | 3
6 | Quentin Sheets |  |  |  | 2 |  |  | 3
7
8
9